SANO

Structured Approval Network & Operations

Mandor & Opname System Audit

Data Structure, Workflow, Control Systems, and Expansion Design

March 2026 | v1.0

For: Wilson Harkhono

# 1. Executive Summary

This audit evaluates the SANO mandor and opname subsystem across four dimensions: data structure integrity, workflow correctness, control system coverage, and UI/UX compliance with the SANO design guideline. It also proposes a concrete architecture for two new payment mechanisms: kasbon (cash advance) and attendance-based (HOK) payments.

### Overall Assessment

| Dimension | Rating | Key Finding |
| --- | --- | --- |
| Data Structure (SQL) | SOLID | Normalized tables, server-side triggers, revision log, cascading recompute |
| Payment Waterfall | SOLID | All math in Postgres RPCs, no client-side computation in production path |
| Workflow / State Machine | SOLID | 5-state lifecycle with role-gated RPCs via assert_project_role() |
| Trade Auto-Detection | GOOD | 3-tier confidence + context override system, bulk tagging via RPC |
| UI / Theme Compliance | GOOD | Consistent use of SANO tokens; minor gaps in accessibility labels |
| Kasbon Tracking | GAP | Single field on opname_headers; no standalone kasbon requests or ledger |
| Attendance / HOK Pay | MISSING | Deprecated Attendance type exists but has no active DB table or UI |
| Progress Reconciliation | GOOD | v_opname_progress_reconciliation cross-checks Gate 4 vs opname claims |

# 2. Data Structure Audit

## 2.1 Table Architecture

The mandor/opname system is implemented across migrations 008 and 011 with the following table hierarchy:

| Table | Purpose |
| --- | --- |
| ahs_lines (extended) | trade_category + trade_confirmed columns for labor classification |
| mandor_contracts | 1 per mandor per project; stores trades[], retention_pct, is_active |
| mandor_contract_rates | Negotiated borongan rate per BoQ item vs frozen AHS labor rate |
| opname_headers | Weekly payment claim; full waterfall fields; 5-state lifecycle |
| opname_lines | Per BoQ-item progress; cumulative/verified/prev %; TDK ACC flag |
| opname_line_revisions | Immutable audit log of every estimator adjustment (011) |

## 2.2 Strengths

■  Frozen rate snapshots: contracted_rate and boq_labor_rate are captured at opname creation, protecting against retroactive rate changes.

■  Generated column: this_week_pct is a STORED generated column ensuring consistency between cumulative and previous percentages.

■  Server-side triggers (011): trg_opname_lines_set_amounts recomputes amounts on every INSERT/UPDATE; trg_opname_lines_recompute_header cascades to header totals.

■  Revision log: opname_line_revisions captures every verified_pct adjustment and TDK ACC toggle with changed_by user ID.

■  Cascading recompute: When an approved opname changes, refresh_opname_headers_for_contract recalculates all future weeks automatically.

■  Variance tracking: v_labor_boq_rates aggregates AHS labor costs per trade per BoQ item, enabling contract-vs-BoQ variance display.

## 2.3 Issues Found

■  Kasbon is a single NUMERIC field on opname_headers. There is no history of when kasbon was taken, who authorized it, or whether it was repaid. If a mandor takes Rp 5M kasbon on Monday but the opname is created on Saturday, there is no mechanism to record that mid-week event.

■  No attendance/HOK table. The types.ts file has a deprecated Attendance interface, and tmp/ has an old CREATE TABLE, but no active migration creates it. Mandors who are paid by daily headcount have no data entry path.

■  opname_headers.kasbon allows negative values. There is no CHECK constraint preventing negative kasbon, which could inflate net_this_week.

■  opname_lines.cumulative_pct has no upper bound CHECK. The SQL allows values > 100. The client clamps to 100, but direct API calls could insert over-progress.

# 3. Workflow & State Machine Audit

## 3.1 Opname Lifecycle

The opname follows a strict 5-state machine enforced server-side:

| Transition | From | To | Who / Controls |
| --- | --- | --- | --- |
| submit_opname | DRAFT | SUBMITTED | supervisor, estimator, admin, principal |
| verify_opname | SUBMITTED | VERIFIED | estimator, admin, principal + promotes verified_pct |
| approve_opname | VERIFIED | APPROVED | admin, principal + sets kasbon, cascades future headers |
| mark_opname_paid | APPROVED | PAID | admin, principal + triggered after Excel export |

## 3.2 Role-Gated Controls

Every RPC calls assert_project_role() which verifies the calling user is assigned to the project AND holds the required role. This is a SECURITY DEFINER function, meaning it runs with elevated privileges but validates auth.uid() internally.

■  DRAFT stage: Only cumulative_pct can be edited. Attempts to set verified_pct or TDK ACC raise exceptions.

■  SUBMITTED stage: Only verified_pct, is_tdk_acc, and notes can be edited. cumulative_pct is locked.

■  VERIFIED/APPROVED/PAID: No line edits permitted at all.

■  verify_opname automatically calls promote_verified_pct to lock in the estimator's adjustments.

## 3.3 Workflow Strengths

■  Separation of concerns: Supervisor proposes, estimator verifies, admin approves. No single role can complete the full cycle alone.

■  Automatic prior_paid computation: get_prior_paid() sums all previous APPROVED/PAID opnames' net_to_date.

■  TDK ACC exclusion: Items marked TDK ACC are excluded from gross_total via FILTER (WHERE NOT is_tdk_acc).

■  Progress reconciliation: v_opname_progress_reconciliation cross-references opname claims against Gate 4 field progress with 5%/15% thresholds.

## 3.4 Workflow Gaps

■  No REJECTED state. If an estimator wants to reject a submission entirely, there is no SUBMITTED -> DRAFT rollback. The estimator can only adjust individual lines. A full rejection workflow should allow sending back to DRAFT with a reason.

■  PAID is auto-triggered after Excel export. If the export succeeds but actual bank transfer fails, the opname is already marked PAID with no rollback path. Consider separating export from payment confirmation.

■  No duplicate week guard on client. The SQL has UNIQUE(contract_id, week_number) but the UI doesn't check before attempting creation. User sees a cryptic Supabase error rather than a friendly message.

# 4. Control & Input System Audit

## 4.1 Input Validation

| Input | Validated? | Notes |
| --- | --- | --- |
| cumulative_pct (client) | YES | Clamped to [prev_cumulative_pct, 100] in handleLineChange |
| cumulative_pct (server) | PARTIAL | opname_effective_pct clamps 0-100, but raw INSERT allows >100 |
| contracted_rate | YES | parseFloat + NaN/<=0 check in handleSaveRate |
| week_number | YES | parseInt + <1 check; DB UNIQUE prevents duplicates |
| kasbon input | PARTIAL | parseFloat with fallback to 0; no max check against net_to_date |
| retention_pct | PARTIAL | parseFloat ¦¦ 10 default; no range check (could be >100 or negative) |
| mandor_name | YES | trim() + empty check; DB UNIQUE(project_id, mandor_name) |
| TDK ACC reason | PARTIAL | Hardcoded default reason; should prompt user for real reason |

## 4.2 Audit Trail Coverage

■  opname_line_revisions captures every verified_pct adjustment and TDK ACC toggle with user ID and timestamp.

■  opname_headers records submitted_by, verified_by, approved_by with timestamps at each transition.

■  No audit trail for kasbon changes. If admin changes the kasbon amount on an approved opname, the old value is overwritten with no record.

■  No audit trail for contract rate changes. Upsert overwrites the previous contracted_rate with no history.

## 4.3 Security (RLS)

■  All four core tables have RLS enabled with project-scoped policies.

■  Migration 011 tightened INSERT policies: opname_headers_insert requires role + project assignment; opname_lines_insert verifies via header join.

■  All workflow RPCs use SECURITY DEFINER + assert_project_role(), preventing direct table manipulation from bypassing role checks.

■  opname_headers and opname_lines have no UPDATE/DELETE RLS policies after migration 011. Updates go through RPCs (SECURITY DEFINER), so this is acceptable, but direct Supabase client .update() calls would fail. This is by design but should be documented.

# 5. Interface & Theme Compliance Audit

## 5.1 Design Token Usage

Both MandorSetupScreen and OpnameScreen correctly import and use all SANO design tokens:

■  COLORS, FONTS, TYPE, SPACE, RADIUS, RADIUS_SM are all imported from workflows/theme.ts.

■  No hardcoded color values except TRADE_COLORS (which are screen-specific semantic colors, acceptable).

■  Font families use FONTS.regular/medium/semibold/bold consistently.

■  Typography sizes follow the TYPE scale (xs=11, sm=13, base=15, md=16).

## 5.2 UI Efficiency Assessment

■  MandorSetupScreen uses a 3-view pattern (trade_review / contracts / rates) with internal tab navigation. This keeps the mandor setup workflow self-contained.

■  OpnameScreen uses list / lines views with contract selector chips. The progress input uses onEndEditing (not onChange), preventing excessive RPC calls during typing.

■  Payment waterfall is rendered inline with the line items, giving immediate visual feedback when progress % changes.

## 5.3 UI Gaps

■  TDK ACC reason is hardcoded. Line 201: reason is always 'Pekerjaan belum memenuhi standar'. The comment says 'Could show an input prompt'. This should be a TextInput.

■  No confirmation before Submit. handleSubmit directly calls the RPC. Unlike handleApprove (which uses Alert.alert), submit has no confirmation dialog.

■  Missing accessibility labels on progress inputs. TextInput fields for cumulative_pct and verified_pct have no accessibilityLabel.

■  Contract rate import alert uses Alert.alert with long text. On small screens, the multi-line import plan summary may be truncated. Consider a modal with scroll.

# 6. Kasbon & Attendance Payment Design

This section addresses your question: when the mandor takes money not by progress but through kasbon (cash advance) or attendance (headcount x days), what controls and structures should be in place?

## 6.1 The Problem

Currently, SANO only supports one payment mode: progress-based borongan (lump sum per BoQ item %). But in Indonesian construction reality, mandors often receive money through two other channels:

■  Kasbon (Cash Advance): Mandor needs cash before the weekly opname is ready (e.g., to pay workers on Wednesday when opname is Saturday). Current system only records kasbon as a deduction on the opname, with no request/approval workflow.

■  Attendance / Harian (Daily Rate): Some mandors (especially for preparatory or cleanup work) are paid by headcount: X orang x Y hari x Z rate/orang/hari. This has no data structure at all.

## 6.2 Proposed: Kasbon Ledger

Replace the single kasbon field with a full ledger table that tracks every cash advance as a standalone event:

| Column | Purpose |
| --- | --- |
| id, project_id, contract_id | Standard FK references linking to the mandor contract |
| amount NUMERIC NOT NULL | Rupiah amount of the cash advance (always positive) |
| kasbon_date DATE | When the cash was actually given (not the opname date) |
| reason TEXT | Why the mandor needs the advance (e.g., 'bayar tukang hari Rabu') |
| status: REQUESTED / APPROVED / SETTLED | 3-state lifecycle with role gates |
| requested_by, approved_by | Audit trail: who asked, who approved |
| settled_in_opname_id UUID NULL | Links to the opname_header that deducted this kasbon |

The payment waterfall changes from:

■  OLD: net_this_week = net_to_date - prior_paid - kasbon (single field)

■  NEW: net_this_week = net_to_date - prior_paid - SUM(approved unsettled kasbon)

When admin approves an opname, all APPROVED but unsettled kasbon entries for that contract are automatically settled (settled_in_opname_id = this opname). This creates a clean paper trail.

## 6.3 Proposed: Attendance (HOK) Payment Table

For mandors paid by daily headcount rather than progress, add an attendance-based payment path:

| Column | Purpose |
| --- | --- |
| id, project_id, contract_id | Standard FK references |
| attendance_date DATE | The specific work day being recorded |
| worker_count INT | Number of workers present that day |
| daily_rate NUMERIC | Agreed Rp per worker per day |
| line_total NUMERIC GENERATED | worker_count x daily_rate (computed column) |
| work_description TEXT | What work was performed (for audit) |
| recorded_by UUID | Supervisor who logged the attendance |
| verified_by UUID NULL | Estimator who confirmed the headcount |
| status: DRAFT / VERIFIED / SETTLED | 3-state: record -> verify -> deduct from opname |
| settled_in_opname_id UUID NULL | Links to the opname that paid for this attendance |

The payment waterfall expands to:

gross_total = SUM(progress-based lines) + SUM(verified attendance lines)

Or alternatively, attendance payments can be treated as a separate payment stream with its own weekly summary, keeping the progress-based opname clean.

## 6.4 Recommended Payment Mode Architecture

Add a payment_mode field to mandor_contracts to declare how each mandor is paid:

| Mode | Payment Basis | Data Source |
| --- | --- | --- |
| borongan | Progress % | opname_lines (cumulative_pct x volume x rate) |
| harian | Attendance | mandor_attendance (worker_count x daily_rate) |
| campuran | Both | Progress lines + attendance lines combined in waterfall |

This lets the system handle mixed scenarios (e.g., a concrete mandor who is borongan for structural work but harian for cleanup crews).

## 6.5 Control Measures for Kasbon

■  Approval gate: Kasbon REQUESTED by supervisor, APPROVED by admin only. This prevents unauthorized cash withdrawals.

■  Ceiling check: SUM(unsettled kasbon) should not exceed a configurable % of the estimated remaining contract value. Default: 30%. Alert if exceeding.

■  Auto-settlement: When opname is APPROVED, all unsettled kasbon for that contract are automatically deducted and linked. No manual matching required.

■  Aging alert: If a kasbon remains unsettled for > 2 opname cycles, flag it on the PrincipalHomeScreen exception dashboard.

## 6.6 Control Measures for Attendance

■  Daily recording window: Attendance can only be recorded for today or yesterday (no backdating beyond T-1). Prevents fabricated records.

■  Estimator verification: Each attendance entry must be verified before it can be settled. Estimator confirms headcount matches site observations.

■  Rate ceiling: daily_rate is constrained to the rate set in mandor_contracts. Supervisor cannot override the agreed rate.

■  Headcount anomaly flag: If worker_count on any day exceeds 150% of the rolling 7-day average, flag as WARNING for estimator review.

■  Photo evidence (optional): Allow supervisor to attach a site photo when recording attendance, similar to Gate 3 receipt photos.

# 7. Recommended Actions

## Priority 1 — Quick Fixes (no schema change)

| # | Action | File | Effort |
| --- | --- | --- | --- |
| 1 | Add CHECK (kasbon >= 0) to opname_headers | migration 013 | 5 min |
| 2 | Add CHECK (cumulative_pct BETWEEN 0 AND 100) to opname_lines | migration 013 | 5 min |
| 3 | Replace hardcoded TDK ACC reason with TextInput prompt | OpnameScreen.tsx | 15 min |
| 4 | Add Alert.alert confirmation before handleSubmit | OpnameScreen.tsx | 5 min |
| 5 | Check for existing week_number before createOpnameHeader | OpnameScreen.tsx | 10 min |
| 6 | Add accessibilityLabel to progress % TextInputs | OpnameScreen.tsx | 5 min |
| 7 | Add retention_pct range CHECK (BETWEEN 0 AND 100) | migration 013 | 5 min |

## Priority 2 — Kasbon Ledger (new migration)

■  Create mandor_kasbon table with REQUESTED / APPROVED / SETTLED lifecycle

■  Add RPC: request_kasbon, approve_kasbon (with ceiling check)

■  Modify approve_opname RPC to auto-settle unsettled kasbon

■  Add KasbonSection component to OpnameScreen (list + request button)

■  Add kasbon aging alerts to PrincipalHomeScreen

Estimated effort: 2-3 days

## Priority 3 — Attendance / HOK Payment (new migration)

■  Create mandor_attendance table with DRAFT / VERIFIED / SETTLED lifecycle

■  Add payment_mode to mandor_contracts (borongan | harian | campuran)

■  Build AttendanceEntryScreen for supervisor daily recording

■  Extend opname waterfall to include verified attendance totals

■  Add headcount anomaly detection (rolling average comparison)

Estimated effort: 4-5 days

## Priority 4 — Separation of Export and PAID

■  Decouple Excel export from mark_opname_paid

■  Add explicit 'Konfirmasi Pembayaran' button after export

■  Optionally add payment_reference field (bank transfer number)

Estimated effort: 1 day

# 8. Conclusion

The SANO mandor and opname system is architecturally strong. The decision to move all payment computation to Postgres RPCs (migration 011) was correct and eliminates an entire class of client-side rounding and race-condition bugs. The trade auto-detection system is well-designed with its confidence tiers and context overrides.

The primary gap is that the system assumes all mandors are paid by progress (borongan), which doesn't reflect the full reality of Indonesian construction site payments. Adding a kasbon ledger and attendance table — both following the same REQUESTED/APPROVED/SETTLED pattern as the existing opname lifecycle — would complete the payment picture without disrupting the existing architecture.

The quick fixes (Priority 1) should be applied immediately as they are low-risk, high-value guardrails. The kasbon and attendance features can be built incrementally, with kasbon being the higher priority since it directly affects existing opname accuracy.

End of Audit Report